## Summary
Fox Cities Racquet Club - Odoo Cost Estimate
Prepared from | BRD PDF v1.0 | BRD Scope Highlights
Currency | USD | • Integrated ERP replacing disconnected systems and manual processes.
Prepared Date | 2026-07-17 | • CRM/customer master with family/household relationships and document history.
Recommended License Plan | Odoo Custom - annual billing | • Membership management with automated renewals and recurring billing.
Planning Paid Users |  | • Court scheduling with conflict prevention, recurring bookings, maintenance blocks, waitlists, and utilization reporting.
Implementation Rate |  | • Programs, lessons, clinics, leagues, instructor scheduling, and attendance tracking.
• POS with barcode scanning, member pricing, gift cards, returns, payments, and immediate inventory/accounting posting.
Cost Summary |  | • Inventory/purchasing/vendor management with receiving, valuation, and AP matching.
Implementation subtotal |  | • Accounting, payroll/HR, role-based security, dashboards, migration, UAT, cutover, and 30-day stabilization.
Implementation contingency
Implementation total
Recommended Odoo license, year 1 |  | Recommendation
Estimated hardware/third-party, upfront |  | Use Odoo Custom plan for costing because the BRD includes custom workflows, Odoo Studio/custom modules, external integrations/API possibility, portal/online booking readiness, and role/security customization. The implementation estimate follows the BRD configuration-first principle and treats custom development as last resort.
Estimated first-year total
Estimated recurring annual license only

## Implementation Cost
WBS | Workstream | BRD Coverage | Scope Included | Odoo Apps / Components | Low Hours | Base Hours | High Hours | Risk | Notes | Base Cost
DISC | Discovery, BRD validation & solution blueprint | All sections | Process workshops, fit-gap, requirements traceability, solution design, backlog, project plan | Project, Knowledge | 60 | 90 | 120 | Medium | Includes validation of 72-page BRD and configuration-first design.
PM | Project management & governance | All workstreams | Status meetings, RAID log, change control, steering reviews, budget/schedule management | Project | 55 | 80 | 110 | Medium | Assumes remote project governance.
BASE | Base Odoo setup & environment configuration | NFR, Security, Maintainability | Company setup, fiscal settings, users, email templates, system parameters, backup/cutover settings | Settings, Discuss, Documents | 35 | 50 | 70 | Low | Odoo.sh/on-prem hosting excluded unless selected.
CRM | CRM, customer records & family relationships | BR-CRM-001 to BR-CRM-005 | Customer master, duplicate controls, household/family links, archive rules, customer history, communications, documents | CRM, Contacts, Documents, Email Marketing | 95 | 135 | 180 | High | Family/household logic may require custom fields and views.
MEM | Membership management & recurring billing | BR-CRM-006, Membership scope | Membership types, privileges, annual/monthly billing, renewals, guest handling, customer balances, statements | Subscriptions, Invoicing, Sales | 90 | 130 | 175 | High | Assumes membership billing mapped to subscriptions/recurring invoices.
COURT | Court scheduling & reservations | BR-COURT-001 to BR-COURT-006 | Courts/resources, reservation calendar, recurring bookings, booking windows, conflict prevention, maintenance blocks, waitlists | Appointments, Planning, Calendar, Website/Portal | 170 | 240 | 330 | High | Largest custom-risk area; Odoo has no out-of-box racquet court scheduler.
PROG | Programs, instruction, lessons, clinics & leagues | Programs and Instruction scope | Private/group lessons, clinics, junior/adult programs, league administration, attendance, instructor assignment | Planning, Events, Sales, Project | 110 | 155 | 220 | High | League scheduling and attendance rules may need custom configuration.
POS | Point of Sale retail operations | BR-POS-001 to BR-POS-006 | POS setup, barcode scanning, member pricing, discounts, gift cards, returns/exchanges, payment flow, customer purchase history | POS, Sales, Payments | 75 | 105 | 145 | Medium | Payment terminal provider setup excluded from license cost.
INV | Inventory & purchasing | BR-INV-001 to BR-INV-006 | Products, SKUs, stock locations, receiving, adjustments, valuation, reorder rules, purchase orders, vendor bills match | Inventory, Purchase, Barcode, Accounting | 95 | 135 | 185 | Medium | Includes retail, teaching, office, and maintenance inventory categories.
ACC | Accounting, AR/AP, GL & bank reconciliation | BR-ACC-001 to BR-ACC-009 | Chart of accounts, AR/AP, customer invoices, payments, reminders, vendor bills, approvals, bank reconciliation, financial statements | Accounting, Invoicing, Approvals | 120 | 165 | 230 | High | Sage 50 reconciliation and opening balances included in migration rows.
PAY | Payroll & HR | BR-ACC-010 to BR-ACC-013 | Employee records, payroll rules, leave balances, payroll approval, GL posting, payroll reporting | Employees, Payroll, Time Off, Approvals | 70 | 105 | 155 | High | US payroll localization/provider dependency may change scope.
DOC | Documents, waivers, contracts & e-signature | BR-CRM-005, Documentation | Document folders, waivers/contracts, attachment rules, document history, e-sign workflow where applicable | Documents, Sign, Contacts | 45 | 70 | 100 | Medium | Assumes standard Odoo Sign where possible.
COMMS | Customer portal & communications | Customer experience, Scheduling, Collections | Portal/customer account visibility, emails, payment reminders, schedule notifications, optional online booking readiness | Portal, Website, Email Marketing, SMS | 65 | 95 | 145 | High | SMS/credit costs excluded. Online booking may need custom build.
RPT | Dashboards, reports & analytics | KPIs, Reporting, NFR-008 | Executive dashboards, court utilization, membership stats, instructor productivity, inventory, financial reports, Excel/PDF exports | Spreadsheet BI, Dashboards, Accounting Reports | 80 | 120 | 170 | Medium | Includes management dashboards and saved filters.
MIG | Data migration & reconciliation | Section 9 Data Migration | Customers, vendors, inventory, memberships, AR/AP, opening GL balances, employee data, cleansing, validation, financial reconciliation | Import tools, Accounting, Inventory | 130 | 185 | 270 | High | Assumes source data provided from Sage 50/spreadsheets in usable exports.
SEC | Roles, permissions & approvals | Section 6 User Roles, NFR-004 | Role-based access for GM, Pro Shop/Accounting, Front Desk/POS, instructors/staff; approval workflows and audit controls | Users, Approvals, Security Groups | 45 | 70 | 100 | Medium | Least-privilege role matrix included.
QA | Testing, UAT & quality assurance | NFR-012, Acceptance Criteria | Unit, integration, migration validation, UAT, POS testing, scheduling validation, financial reconciliation, regression testing | Project, Test scripts | 100 | 145 | 210 | High | Includes UAT support and defect triage.
TRAIN | Training & change management | Documentation, User adoption KPI | Admin training, front desk/POS training, accounting training, instructor/program workflows, user guides, quick reference material | Knowledge, Odoo eLearning | 65 | 95 | 135 | Medium | Remote training assumed. Onsite travel excluded.
GO | Cutover, go-live & 30-day stabilization | Cutover Strategy, Overall Acceptance | Go-live checklist, final migration, freeze window, contingency plan, launch support, 30-day stabilization | All modules | 70 | 105 | 150 | High | Includes post-go-live support window.
Implementation subtotal
Contingency
Implementation total

## Odoo License Cost
Odoo License Cost - USD
Planning paid internal users | 12 | Editable. BRD lists roles but not exact headcount. Customer/member portal users are not paid users.
Standard annual billing price per user/month | 24.9 | USD, annual billing list rate used for planning.
Standard monthly billing price per user/month | 31.1 | USD, month-to-month rate used for comparison.
Custom annual billing price per user/month | 37.4 | USD, annual billing list rate used for recommendation.
Custom monthly billing price per user/month | 46.8 | USD, month-to-month rate used for comparison.
Plan Scenario | Included | Billing | Monthly Cost | Annual Cost | Notes
One App Free | One app, unlimited users, Odoo Online | N/A |  |  | Not suitable for BRD because multiple apps are required.
Standard | All apps, Odoo Online | Annual billing |  |  | Comparison only; not recommended if custom modules/API/Studio are required.
Standard | All apps, Odoo Online | Monthly billing |  |  | Comparison only.
Custom - Recommended | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Annual billing |  |  | Recommended for BRD because custom workflows, integrations and Odoo Studio/custom development are likely.
Custom | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Monthly billing |  |  | Comparison only.
Odoo.sh hosting | Continuous integration hosting for custom modules | Quote required |  |  | Not included in Odoo license cost; add once hosting decision is made.
License Notes
• Official Odoo pricing page states Standard and Custom include all apps for a single fee and all plans include support, hosting and maintenance.
• Odoo pricing page notes implementation services, in-app purchase credits, Odoo.sh hosting for custom developments, and custom code maintenance are not included in license pricing.
• Paid users are internal users accessing backend records. Customer/member portal users are not included as paid users per Odoo pricing FAQ.
• Final subscription quote should be validated with Odoo/Odoo partner before contract signature because pricing and region/currency can change.

## Hardware & Third Party
Category | Item | Qty | Unit Cost USD | Estimated Cost | Notes
POS Hardware | Barcode scanners | 2 | 175 |  | Needed for BR-POS-001. Final model depends on POS device.
POS Hardware | Receipt printers | 2 | 300 |  | Estimate only.
POS Hardware | Cash drawers | 2 | 150 |  | Estimate only.
POS Hardware | Label printer for inventory/barcodes | 1 | 450 |  | Useful for inventory SKU/barcode labels.
POS Hardware | POS terminal/tablet/computer allowance | 2 | 850 |  | Use existing hardware if compatible.
Payments | Payment terminals | 2 | 0 |  | Processor/provider quote required; not included.
Communications | SMS / IAP credits | 1 | 0 |  | Odoo in-app purchase credits excluded from license.
Payroll | US payroll provider/subscription | 1 | 0 |  | Provider cost and compliance model to be confirmed.
Data | Sage 50 export/support assistance | 1 | 0 |  | May be handled by client or vendor.
Travel | Onsite travel and expenses | 1 | 0 |  | Remote implementation assumed. Add if onsite required.
Contingency | Hardware contingency | 1 |  |  | 10% hardware contingency.
Total

## Phasing
Phase | BRD Priority | Workstreams | Target Outcome | Estimated Base Hours | Estimated Cost | Notes
Phase 0 | Initiation | Discovery, blueprint, project governance, base setup | Validated solution design, backlog, environment readiness |  |  | Before configuration build.
Phase 1 | Core Operations | CRM, memberships, court scheduling, programs, POS, inventory, AR/customer billing | Front desk and daily operational workflows ready for UAT |  |  | Matches BRD Phase 1 core operations.
Phase 2 | Financial Management | Purchasing, AP, GL, bank reconciliation, payroll/HR, approvals | Financial workflows and payroll/HR aligned to accounting close |  |  | Matches BRD Phase 2 and security requirements.
Phase 3 | Reporting & Documents | Documents, Sign, communications, portal, dashboards, reports | Management visibility and customer-facing communication flows |  |  | Includes optional online booking readiness.
Phase 4 | Migration, QA & Go-Live | Data migration, testing, training, cutover, stabilization | Validated migration, UAT acceptance, go-live, 30-day stabilization |  |  | Final acceptance criteria and cutover.
Subtotal by phases

## Assumptions
Assumptions and Exclusions
Implementation hourly rate USD | 95 | Editable
Implementation contingency % | 10% | Editable
Paid internal users | 12 | Editable in Odoo License Cost sheet
Key Assumptions
• The BRD is used as the pricing scope baseline; detailed fit-gap may change estimates.
• Configuration-first approach is assumed; custom development is limited to gaps not covered by standard Odoo, Studio, or supported modules.
• 12 paid internal users are assumed because the BRD defines roles but not exact staff count. Customer/member portal users are assumed free under Odoo pricing rules.
• Odoo Custom annual plan is recommended for budgeting due to custom modules/workflows, Odoo Studio/customization, API/integration possibility, and future online booking requirements.
• US payroll feasibility depends on chosen payroll method/provider and compliance requirements.
• Payment processor/terminal costs, SMS/IAP credits, Odoo.sh hosting, custom-code maintenance, and onsite travel are excluded unless explicitly added.
• Data migration estimate assumes client supplies usable Sage 50 exports, spreadsheets, and cleansed source files in agreed formats.
• Hardware estimates are placeholders and should be validated against selected POS devices and payment processor.
• All amounts are in USD and are planning estimates, not a binding quotation.
Out of Scope Unless Added by Change Order
• Website redesign/redevelopment beyond standard Odoo portal/website setup.
• Native mobile application development.
• Building automation systems and telephone system replacement.
• Non-Odoo custom software unrelated to documented BRD requirements.
• Historical transaction migration beyond agreed opening balances and active operational data.
• Ongoing managed support after 30-day stabilization unless contracted separately.

## Sources
Source | URL / File | Used For | Notes
BRD PDF | Fox Cities Racquet Club - Odoo Business Requirements Document v1 (1).pdf | Implementation scope, workstreams, migration, roles, acceptance criteria | Downloaded from attached signed URL on 2026-07-17.
Odoo Pricing | https://www.odoo.com/pricing | Plan inclusions, all-app pricing model, plan limitations/exclusions, paid user rule | USD license rates used in workbook: Standard $24.90/$31.10 and Custom $37.40/$46.80 per user/month for annual/monthly billing. Confirm final quote with Odoo/partner.
Odoo Success Packs | https://www.odoo.com/pricing-packs | Benchmark reference for implementation activities and Odoo service exclusions | Used as reference only; this workbook uses partner-style workstream estimate.