## Summary
Fox Cities Racquet Club - BRD Implementation Cost Sheet
Prepared from attached BRD/SOW dated 2026-07-17. Currency: USD. Summary shows implementation services only.
Prepared for | Fox Cities Racquet Club |  | Cost Basis | Attached BRD/SOW implementation scope
Prospect address | Fox Cities Racquet Club 2915 N. Victory Lane Appleton, WI 54913 |  | Source | foxcitiesracquetclub.com Location/Hours
Phone | 920.739.0221 |  | Website | https://www.foxcitiesracquetclub.com/
Prepared date | 2026-07-17 |  | Implementation rate
Currency |  |  | Contingency | Removed
Cost Summary | Monthly Equivalent | One-Time | Notes
Estimated implementation total |  |  | Implementation services only; no contingency buffer included.
Payment Terms
Milestone | Percentage | Amount | Notes
Advance payment | 50% |  | Due before project kickoff.
On UAT | 35% |  | Due on UAT readiness / UAT start.
On go live | 15% |  | Due on production go-live.
Total |  |  | Matches implementation total.
Key Exclusions | Hardware and IoT devices are not included. Any third-party connectivity will be studied and quoted separately.
Implementation Scope Highlights
Custom court booking configuration, dashboard validation, conflict prevention, lifecycle, no-show indicators and booking invoicing.
Membership plans, membership year, prorated invoice wizard, member/non-member status and one-active-membership validation.
Retail product, inventory, purchase, sales, POS and barcode setup for pro-shop operations.
Accounting setup/validation for booking, membership, sales, POS and purchase flows.
CRM stages/opportunities, reporting pack, UAT, training and handover.

## Implementation Cost
Implementation Cost Estimate - Attached BRD Scope
Planning estimate only. Hardware, IoT devices, and third-party connectivity are excluded. Odoo subscription license remains on the separate license sheet and is not included in the implementation total.
WBS | Phase / Workstream | BRD Reference | Scope Included | Odoo Apps / Components | Low Hours | Base Hours | High Hours | Rate | Base Cost | Risk | Notes
DISC | Discovery and confirmation | 15 Phase 1 | Confirm courts, capacities, billing basis, operating hours, membership plans/prices/year, non-member fee, ball machine rate, product categories, POS payments and accounting mappings. | Project, Knowledge | 24 | 32 | 44 |  |  | Medium | Includes configuration workbook, process maps and demo data list.
PM | Project management and governance | All phases | Status meetings, RAID/change control, schedule coordination, UAT tracking and delivery administration. | Project | 25 | 35 | 50 |  |  | Medium | Remote governance assumed.
BASE | Base Odoo setup and access rights | 1, 14, 15 | Company settings, users, role/security baseline, apps readiness, email/basic system setup and standard module installation checks. | Settings, Contacts, Discuss | 18 | 24 | 34 |  |  | Low | Does not include Odoo subscription or hosting fees.
COURT | Custom court booking configuration and validation | 3, 4, 13.1, 13.2 | Configure courts, seat capacity, person/hour vs court/hour policies, rates, dashboard availability, conflict prevention, lifecycle states, start/end rules, no-show indicators and reminders. | Custom FCRC Court Seat Booking, Accounting, Product, Web, Mail | 70 | 95 | 135 |  |  | High | Main custom-risk area; assumes the core custom module already exists and is being configured/validated for this demo scope.
MEM | Membership configuration and invoicing | 5 | Membership years, plans, auto-created service products, proration rules, one-active-membership validation, member/non-member menus and booking pricing behavior. | Contacts, Invoicing, Product, Custom membership models | 38 | 52 | 74 |  |  | High | Family eligibility automation is excluded per BRD.
BILL | Booking billing and accounting integration | 4.8, 10, 15 Phase 4 | Income account mapping, court invoice lines, non-member entry fees, ball machine lines, invoice smart button/linkage, draft invoice delete behavior, posted invoice controls and scheduled-hours billing validation. | Accounting, Invoicing, Custom booking module | 35 | 48 | 70 |  |  | High | Tax and revenue-account mapping require client approval.
INV | Retail product and inventory setup | 6, 15 Phase 5 | Product categories, stockable retail products, SKU/barcode fields, sales/cost prices, initial quantities, vendors where available, reorder rules and stock availability review. | Inventory, Product, Barcode | 36 | 50 | 70 |  |  | Medium | Physical inventory count and hardware are excluded.
PUR | Purchase setup | 9, 15 Phase 6 | Vendor setup, vendor prices, RFQ/PO workflow, receipts into stock, vendor bill creation and purchase-to-accounting validation. | Purchase, Inventory, Accounting | 18 | 26 | 38 |  |  | Medium | Vendor catalog integration, if any, is separate.
SALES | Sales setup | 7, 15 Phase 7 | Sales quotation flow, retail product sales orders, sales order invoice validation, customer sales history and optional templates for group/corporate quotes. | Sales, Invoicing, Contacts | 16 | 24 | 34 |  |  | Low | Event/group booking automation beyond quote flow is excluded.
POS | Point of Sale setup | 8, 15 Phase 8 | POS shop/session, POS product categories, retail product availability, payment methods, POS sale validation, inventory deduction and accounting entry generation. | Point of Sale, Inventory, Accounting | 24 | 34 | 50 |  |  | Medium | Payment terminals and processor fees are excluded.
BAR | Barcode setup | 11, 15 Phase 9 | Barcode policy, barcode values on stockable products, scanning validation in POS, receipts and inventory adjustments, label-needs review. | Barcode, Inventory, POS | 14 | 20 | 30 |  |  | Medium | Complex barcode label templates and scanners are excluded.
CRM | CRM setup | 12, 15 Phase 10 | CRM stages, lead sources, sample opportunities, lead-to-contact conversion, quote/membership follow-up process. | CRM, Sales, Contacts | 14 | 20 | 30 |  |  | Low | Marketing automation/campaign spend is excluded.
RPT | Reports and dashboards | 13, 15 Phase 11 | Booking pivot/graph/list analysis, operational queues, daily summary review, and validation of standard accounting, sales, POS, inventory and purchase reports. | Reporting, Dashboards, Accounting, Sales, Inventory, POS | 24 | 34 | 50 |  |  | Medium | Custom BI/warehouse dashboards are excluded.
UAT | Testing and user acceptance | 15 Phase 12, 18 | UAT checklist and execution support for booking, membership, POS, sales, purchase, barcode, CRM and accounting scenarios; issue log and sign-off support. | All implemented apps | 30 | 42 | 60 |  |  | Medium | Includes demo-scope UAT, not full historical parallel run.
TRN | Training and handover | 15 Phase 13 | User training for court dashboard, booking lifecycle, membership invoicing, POS, inventory, purchase, accounting, CRM, reports; admin handover and basic guide. | All implemented apps | 16 | 24 | 34 |  |  | Low | Remote training assumed.
Implementation subtotal
Estimated implementation total
Note on G5: Base hours are planning estimates. Edit low/base/high hours to revise costs.

## Odoo License Cost
Odoo License Cost - Separate Sheet
License subscription estimate only. Implementation services, hardware, IoT, Odoo.sh/hosting, IAP/SMS credits, payment terminals and third-party connectivity are excluded.
Input | Value | Notes
Planning paid internal users |  | Editable in Assumptions. BRD lists roles but not exact user count.
Standard annual list/user/month USD | 24.9 | Comparison only; not recommended for custom module/Odoo.sh deployment.
Standard monthly list/user/month USD | 31.1 | Comparison only.
Custom annual list/user/month USD | 37.4 | Recommended planning rate for Custom plan.
Custom monthly list/user/month USD | 46.8 | Month-to-month comparison only.
Plan Scenario | Included | Billing | Monthly Equivalent | Annual Cost | Recommended | Notes
Standard - annual list | All apps, Odoo Online | Annual |  |  | No | Comparison only; no custom modules/Odoo.sh custom-code hosting.
Standard - monthly list | All apps, Odoo Online | Monthly |  |  | No | Comparison only.
Custom - annual list | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Annual |  |  | Yes | Recommended for this BRD because the scope uses a custom court booking module and custom workflows.
Custom - monthly list | All apps, Custom plan | Monthly |  |  | No | Comparison only; annual billing is usually cheaper.
License Notes | Details
Backend users | Only internal/staff backend users are counted in this planning sheet; website/customer portal users are not treated as paid backend users.
Official quote | Final Odoo license cost must be confirmed by Odoo or the selling partner for the billing country and contract term.
Separate from implementation | Implementation estimate is on the Implementation Cost sheet and is not included here.
Note on B5: BRD lists roles, not named user count. Update Assumptions if FCRC confirms a different number.

## Assumptions
Assumptions and Editable Inputs
Assumption | Value | Notes
Currency | USD | All implementation and license figures are shown in USD.
Implementation hourly rate USD | 28 | Editable blended remote delivery planning rate.
Contingency buffer | Removed | No contingency buffer is applied per customer request.
Planning paid internal users | 5 | Editable. BRD lists roles but does not provide exact named users.
Recommended Odoo plan | Custom - annual billing | Recommended because the BRD includes custom court booking module usage and custom/advanced configuration.
License pricing basis | Planning estimate | Confirm final Odoo subscription quote with Odoo or selling partner before contract.
Scope source | fcrc_brd_scope_of_work.pdf dated 2026-07-17 | Attached BRD/SOW is the scope baseline for this workbook.
Delivery model | Remote implementation | Onsite travel and expenses are excluded.
Data ownership | Client-provided master data | Court list, rates, memberships, products, vendors, taxes, accounts and opening quantities must be provided/approved by FCRC.
Third-party connectivity | Excluded | Any third-party integration/connectivity will be studied and quoted separately.
Hardware and IoT | Excluded | Barcode scanners, POS terminals, printers, payment terminals, court access/lighting IoT and networking hardware are not included.
Post-go-live support | 30-day stabilization included | Managed support after stabilization is separate.

## BRD Traceability
BRD Traceability to Cost Lines
BRD Section | Scope Area | Cost WBS | Workbook Treatment
1-2 | Executive summary and business objectives | DISC, PM, BASE | Included in discovery, base setup and governance.
3 | Current custom module overview | COURT | Configured and validated as implementation scope; not priced as hardware or third-party.
4 | Court booking requirements | COURT, BILL, RPT, UAT | Included for dashboard, lifecycle, validations, billing and reporting validation.
5 | Membership requirements | MEM, BILL, UAT, TRN | Included for membership plans, year, invoicing and statuses.
6 | Retail inventory requirements | INV, BAR, POS | Included for products, stock, reorder rules and barcode-ready product master.
7 | Sales module scope | SALES | Included for quotations, sales orders, invoices and order history.
8 | Point of Sale scope | POS, BAR | Included for POS setup and process validation; POS hardware/payment terminals excluded.
9 | Purchase module scope | PUR | Included for vendor/RFQ/PO/receipt/vendor bill flow.
10 | Accounting module scope | BILL, BASE, UAT | Included for invoices, payments, AR/AP, account mapping and standard reporting readiness.
11 | Barcode scope | BAR | Included for barcode data and scan validation; scanners and complex label templates excluded.
12 | CRM scope | CRM | Included for stages, sources, sample opportunities and conversion flow.
13 | Reporting requirements | RPT | Included for booking analysis, operational dashboard and standard reports.
14 | User roles | BASE, TRN | Included in access baseline and handover.
15 | Detailed scope of work | All WBS | Cost sheet follows BRD phases 1-13.
16 | Out of scope for current demo | Exclusions | Excluded unless separately approved.
17-20 | Assumptions, acceptance, risks, next steps | DISC, UAT, PM | Reflected in assumptions, UAT and risk notes.

## Exclusions & Notes
Exclusions and Commercial Notes
Category | Included in Cost? | Treatment | Notes
Hardware and IoT devices | No | Excluded | Barcode scanners, receipt printers, cash drawers, POS terminals/tablets, label printers, payment terminals, court lighting/access control, networking and other IoT devices are not included.
Third-party connectivity | No | Separate study and quote | Any payment gateway, bank feed, vendor catalog, SMS/email service, external website, access control, Sage/legacy connectivity or API integration will be studied and quoted separately.
Odoo license | Separate sheet | Estimated separately | See Odoo License Cost sheet. License is not part of the implementation service total.
Odoo.sh / hosting | No | Quote separately if required | Hosting is not included in the implementation total or license sheet unless separately quoted.
Online portal booking / website checkout | No | Out of scope | Excluded by BRD section 16 unless separately approved.
Payment gateway integration | No | Out of scope / separate quote | Processor setup, payment terminals and transaction fees are excluded.
Automated recurring membership billing | No | Out of scope | Excluded by BRD section 16.
Family member eligibility automation | No | Out of scope | Family handling remains operational outside ERP for the demo per BRD.
Advanced lessons, leagues and tournaments | No | Out of scope | Advanced coaching/lesson scheduling and league/tournament management are excluded by BRD section 16.
Payroll | No | Out of scope | Not listed in current implementation scope and excluded from this cost sheet.
Complex barcode label printing templates | No | Out of scope | Basic barcode fields and scan validation are included; complex template design is excluded.
Data migration beyond setup/demo data | No | Separate quote if needed | The BRD focuses configuration/demo readiness. Historical transaction migration is not included unless separately scoped.