## Summary
Fox Cities Racquet Club - Odoo Meeting Cost Estimate
Prepared from July 15, 2026 meeting notes and available BRD scope. Currency: USD.
Prepared for | Fox Cities Racquet Club |  | Recommended Direction
Prospect contact | Dean Verstegen |  | Use Odoo Custom with Odoo.sh because the meeting includes custom court dashboard work and custom modules. Odoo.sh hosting is separate from the license.
Prepared date | 2026-07-17 |  | Current paid users | 5
Currency | USD |  | Implementation model | Remote hourly estimate
Planning hourly rate |  |  | Odoo.sh baseline | 1 worker, 50 GB storage, 1 staging env
Cost Summary - Meeting MVP
Line Item | Monthly Equivalent | Annual / One-Time | Notes
Implementation subtotal |  |  | Base-hour estimate before contingency.
Implementation contingency |  |  | 15% planning contingency.
Implementation total |  |  | One-time implementation budget for meeting MVP.
Odoo Custom license - first-year promo |  |  | 5 paid users, annual billing monthly equivalent.
Odoo Custom license - renewal/list |  |  | Conservative recurring budget after first-year discount period.
Odoo.sh hosting - with staging |  |  | 1 worker + 50 GB + 1 staging environment.
Estimated first-year total - promo license |  |  | Implementation + first-year discounted license + Odoo.sh hosting.
Estimated first-year total - list license |  |  | Same implementation scope using list/renewal license price.
Recurring annual license + hosting after year 1 |  |  | Odoo Custom renewal/list license + Odoo.sh hosting only; excludes implementation and optional support.
Meeting Scope Highlights
Court booking with hourly rates, ball machine, start/end controls, 15-minute validation buffer, seasonal rates, and non-member booking limits.
Custom court dashboard modeled after current court sheets/Excel workflow, pending high-resolution court-sheet images from Dean.
Membership plans with prorated billing, member vs non-member logic, invoices, payments, and account balances.
POS retail setup with products enabled for POS by default, barcode flow, cash closing, gift cards, coupons, and member pricing readiness.
Accounting, bank/payment provider integration, purchase orders, inventory reporting, and optional Odoo website replacement.

## Implementation Cost
Meeting-Based Implementation Estimate
Editable hourly rate and contingency are on the Assumptions sheet. This is a planning estimate, not a fixed quote.
WBS | Workstream | Meeting Requirement | Scope Included | Odoo Apps / Components | Low Hours | Base Hours | High Hours | Rate | Base Cost | Risk | Notes
DISC | Discovery, BRD validation & solution blueprint | Review 72-page BRD; confirm board-priority scope | Fit-gap workshops, current workflow review, implementation backlog, phase plan | Project, Knowledge | 30 | 45 | 65 |  |  | Medium | Required before final fixed-price commitment.
PM | Project management & governance | Board proposal and contract initiation | Status meetings, RAID log, change control, budget and schedule tracking | Project | 25 | 40 | 60 |  |  | Medium | Remote governance assumed.
BASE | Odoo.sh/base environment setup | US localization, users, settings, email | Company setup, users/security baseline, mail, technical settings, Odoo.sh repo/deployment readiness | Settings, Discuss, Odoo.sh | 25 | 35 | 50 |  |  | Low | License/hosting costs are separate.
ACC | Accounting, invoicing, payments & bank setup | Accounting demo, Sage chart mapping, payment providers | US localization, journals, taxes, payment terms, bank sync readiness, payment provider setup, invoice/payment workflow | Accounting, Invoicing, Payments | 40 | 60 | 90 |  |  | High | Sage migration depth can change cost.
MEM | Membership plans & prorated billing | Adult/family plans, prorated invoices, member/non-member | Membership products, recurring/prorated billing, member status logic, invoices, payments, balances | Subscriptions, Sales, Invoicing | 45 | 70 | 105 |  |  | High | Privilege rules should be confirmed in fit-gap.
COURT | Court booking configuration | $28 court rate, ball machine, seasonal rates, limits | Courts/resources, time slots, capacity, seasonal pricing, 15-minute validation buffer, non-member annual limit, booking-to-invoice flow | Appointments, Calendar, Sales | 70 | 110 | 165 |  |  | High | Reservation rules are the main business-critical area.
DASH | Custom court sheet dashboard | Interactive dashboard modeled on current Excel/paper sheet | Daily court grid, court/time view, booking status, staff actions, start/end play flow, billing handoff | Custom Odoo module, OWL/views | 90 | 140 | 220 |  |  | High | Needs HD current court-sheet images before final sizing.
POS | Point of Sale retail workflow | Products available in POS by default; gifts/coupons | POS shop setup, product default enablement, barcode flow, cash register closing, coupons, gift cards, member pricing readiness | POS, Barcode, Loyalty | 30 | 50 | 75 |  |  | Medium | Payment terminal hardware/fees excluded.
INV | Inventory & purchasing | Purchase orders, stock and forecast reporting | Products/SKUs, stock locations, vendor records, purchase orders, receipts, basic inventory reports | Inventory, Purchase | 25 | 45 | 70 |  |  | Medium | Assumes clean product/vendor list.
WEB | Website and portal foundation | Replace outdated website if requested | Basic Odoo website structure, member-facing pages, portal readiness, contact/forms content migration | Website, Portal | 35 | 60 | 95 |  |  | Medium | Full marketing redesign or custom theme can be quoted separately.
DATA | Data import and migration | Current data, Sage/spreadsheets, members/products | Customer/member import, products, vendors, chart/opening balances, data validation support | Import tools, Accounting, Contacts | 45 | 70 | 120 |  |  | High | Depends heavily on source export quality.
RPT | Dashboards and reporting | Board visibility and operational reporting | Court utilization, membership KPIs, POS sales, inventory, accounting reports, saved filters | Dashboards, Spreadsheet BI | 25 | 45 | 80 |  |  | Medium | KPI definitions to be confirmed.
QA | Testing, UAT, training and go-live | Board/demo readiness and operational adoption | Test scripts, UAT support, staff training, go-live checklist, defect triage | Project, Knowledge | 60 | 95 | 145 |  |  | High | Includes remote training.
SUP | 30-day stabilization support | Support after launch | Post-go-live support, minor fixes, workflow tuning, admin handover | All modules | 30 | 45 | 70 |  |  | Medium | Ongoing managed support is separate.
Implementation subtotal
Contingency
Implementation total

## Odoo License & Hosting
Odoo License and Odoo.sh Hosting - USD
Uses 5 paid internal users. Portal/customer users are not counted as paid backend users.
Input | Value | Notes
Paid internal users | 5 | User request. Member/customer portal users are assumed free.
Standard annual first-year promo/user/month | 19.9 | Comparison only; annual billing monthly equivalent.
Standard annual list/user/month | 24.9 | Comparison only.
Custom annual first-year promo/user/month | 29.9 | Recommended first-year price if current discount applies.
Custom annual list/user/month | 37.4 | Recommended conservative/renewal price.
Custom monthly list/user/month | 46.8 | Month-to-month comparison.
Plan Scenario | Included | Billing | Monthly Equivalent | Annual Cost | Notes
Standard - first-year promo | All apps, Odoo Online | Annual |  |  | Comparison only; not suitable for custom Python modules on Odoo.sh.
Standard - annual list | All apps, Odoo Online | Annual |  |  | Comparison only.
Custom - first-year promo | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Annual |  |  | Recommended for year-1 budgeting if current promotion applies.
Custom - annual list/renewal | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Annual |  |  | Recommended conservative budget and recurring renewal planning.
Custom - monthly list | All apps, Custom plan | Monthly |  |  | Comparison only.
Odoo.sh Component | Qty | Unit Price / Month | Monthly Equivalent | Annual Cost | Notes
Worker | 1 | 57.6 |  |  | Annual billing monthly equivalent. Shared hosting baseline.
Storage (GB) | 50 | 0.2 |  |  | 50 GB matches meeting estimate basis.
Staging environment | 1 | 14.4 |  |  | Recommended for testing custom court dashboard changes.
Odoo.sh total with staging |  |  |  |  | This does not include the Odoo Enterprise license.
Odoo.sh total without staging |  |  |  |  | Matches the approximate $811/year figure discussed in the meeting.
License and Hosting Notes
Odoo.sh is separate from the Enterprise license. The Odoo.sh hosting price does not include the Odoo Enterprise license.
Custom plan is recommended because Odoo.sh/custom Python modules and external API/customization needs are in scope.
Current Odoo first-year discounts can change; use the list/renewal price for conservative board budgeting.
The Odoo.sh worker/storage/staging numbers should be rechecked before contract signature and increased if public online booking traffic grows.
Note on B8: Current first-year promotional annual-billing monthly equivalent used for planning. Validate final rate with Odoo before contracting.
Note on B9: Conservative list/renewal annual-billing monthly equivalent for Odoo Custom.
Note on C21: Annual-billing monthly equivalent from Odoo.sh pricing.
Note on C22: Annual-billing monthly equivalent from Odoo.sh pricing.
Note on C23: Annual-billing monthly equivalent from Odoo.sh pricing.

## Full BRD Expansion
Full BRD Expansion Budget Guide
Optional view if the complete 72-page BRD is implemented as a larger program rather than only the meeting MVP.
Scenario | Low Hours | Base Hours | High Hours | Low Cost | Base Cost | High Cost | Notes
Full BRD implementation | 1575 | 2275 | 3200 |  |  |  | Based on the available BRD review estimate in the workspace.
Contingency | [6 empty] | Planning contingency.
Full BRD implementation total | [6 empty] | Implementation only; excludes license, Odoo.sh, hardware, processor fees, SMS credits, and post-stabilization support.
Full BRD first-year total - base | [6 empty] | Base implementation + Custom first-year promo license + Odoo.sh with staging.
Full BRD Workstreams Included
CRM/customer master, household/family relationships, documents and customer communication history.
Membership management, recurring billing, statements, guest/non-member privileges, and portal readiness.
Court scheduling, programs/lessons/clinics/leagues, instructor scheduling, waitlists, utilization analytics.
POS, barcode, gift cards/coupons, inventory, purchasing, accounting, Sage data migration, reports, roles and approvals.
Payroll/HR scope remains dependent on selected US payroll provider/compliance approach.

## Meeting Scope
Meeting Notes - Requirements Used for Estimate
Extracted from the downloaded Gemini notes and aligned to the available BRD.
Area | Meeting Requirement | Costing Interpretation | Priority
Court booking | $28 hourly court rate; full court or per-seat booking; start/end play cycle; 15-minute buffer validation. | Configure court resources, booking products, validation rules, and billing handoff. | High
Custom dashboard | Interactive court scheduling dashboard modeled after current Excel/court sheet. | Custom module/dashboard is the highest-risk build item and requires current sheet images. | High
Membership | Adult/family membership plans, prorated billing, members vs non-members, annual non-member booking limit. | Configure plans, recurring/prorated invoices, membership status, and booking privileges. | High
POS | Products should default to available in POS; barcode, cash payments, closing, gift cards and coupons demonstrated. | Configure POS and small customization/automation for product POS availability defaults. | Medium
Accounting | US localization/USD, invoices, bills, bank integration, PayPal/payment provider, Sage chart migration discussion. | Accounting setup, payment provider config, CoA/Sage mapping, reconciliation workflow. | High
Inventory/Purchase | Purchase quotations, vendors, product tracking, free stock and forecast reporting. | Product/vendor setup, purchase flow, receiving, stock rules, reports. | Medium
Website | Existing site is outdated and current hosting is about $12/month; Odoo website may replace it if requested. | Include foundation-level Odoo website/portal setup; full redesign remains optional. | Medium
Hosting | Odoo.sh and Deploy ERP discussed; request specifically asks for Odoo.sh pricing. | Use Odoo.sh shared hosting estimate: 1 worker, 50GB, 1 staging env. | High
Engagement | Hourly billing package vs fixed price discussed; board needs ballpark estimate. | Workbook uses editable hourly-rate planning estimate; fixed price requires final scope sign-off. | High

## Assumptions
Assumptions and Exclusions
Edit the rate, contingency, users, and hosting quantities to revise totals.
Assumption | Value | Notes
Currency | USD | All amounts are shown in USD.
Implementation hourly rate USD | 28 | Editable planning rate based on remote delivery. Update this cell to change implementation totals.
Implementation contingency % | 15% | Editable contingency for unknowns, fit-gap, data quality, and custom dashboard risk.
Paid internal users | 5 | User request. Customer/member portal users are excluded from paid backend user count.
Recommended Odoo plan | Custom - annual billing | Needed for Odoo.sh/custom modules, Studio-style customization, multi-company/API availability.
Odoo.sh baseline | 1 worker, 50 GB, 1 staging | Shared hosting estimate for small internal team and testing custom code. Scale if public traffic grows.
Quote type | Planning estimate | Not a binding quote. Fixed price needs signed scope, sample data, and HD court sheet images.
Scope source | Meeting notes + available BRD | Meeting notes drive MVP; full BRD tab shows broader program budget.
Website | Foundation only | Full brand redesign, copywriting, custom theme, SEO campaign, and media production are excluded unless added.
Payment/SMS/IAP | Excluded | Payment processor charges, terminals, SMS credits, lead credits, AI document credits, and third-party app fees are excluded.
Hardware | Excluded | Barcode scanners, receipt printers, cash drawers, tablets, POS terminals, and networking hardware are excluded.
Data migration | Limited active data | Historical transaction migration beyond agreed opening balances and active operational data is excluded.
Payroll | To confirm | US payroll compliance/provider approach must be confirmed before final payroll implementation cost.
Support | 30-day stabilization included | Managed support after stabilization is separate.

## Sources
Sources and Pricing References
Pricing should be validated again with Odoo before contract signature because regional prices and promotions can change.
Source | Reference | Use in Estimate
Meeting notes PDF | Odoo ERP Demo _ Dean Verstegen _ Fox Cities Racquet Club - 2026_07_15 19_59 IST - Notes by Gemini.pdf | Primary source for meeting decisions, next steps, and demo requirements.
Available BRD | Fox Cities Racquet Club - Odoo Business Requirements Document v1 (1).pdf / .txt | Used to validate broader scope and optional full-BRD expansion budget.
Official Odoo pricing | https://www.odoo.com/pricing | Custom plan includes all apps plus Odoo.sh/on-premise option, Studio, multi-company and external API; Odoo.sh hosting is not included in license.
Official Odoo configurator | https://www.odoo.com/pricing-configurator | Used for Custom/Standard annual and monthly planning rates; final quote should be confirmed by billing country.
Official Odoo.sh pricing | https://www.odoo.sh/pricing | Used for Odoo.sh workers, storage, staging environment, and hosting-excludes-license note.
Read-only system check | Configured Odoo database company currency is USD. | Confirmed the configured demo context is USD without creating or modifying records.