## Summary
Fox Cities Racquet Club - BRD Review & India-Based Odoo Cost Estimate
Item | Value |  | Executive Review
Prepared from | Fox Cities Racquet Club BRD PDF v1.0 |  | - BRD is broad and valid for an integrated Odoo ERP, but court scheduling is the main custom-risk area.
Prepared date | 2026-07-17 |  | - Odoo can cover CRM, contacts, subscriptions, POS, inventory, purchase, accounting, documents, approvals, reporting and HR with configuration plus targeted custom work.
Delivery model | India offshore/remote implementation |  | - Membership rules, family/household accounts, court booking windows, league schedules, waitlists, and utilization reporting require deeper fit-gap workshops.
Commercial currency | USD quote with INR reference |  | - US payroll, payment terminals, Sage 50 migration, and online member booking should be confirmed before final quote.
FX assumption | 1 USD = INR 83.50 (editable) |  | - India-based delivery materially reduces implementation cost compared with a US-rate estimate; license cost remains vendor/subscription driven.
Recommended Odoo plan | Custom, annual billing
Planning paid users | 12
Cost Summary - India Delivery
Line Item | USD | INR Reference
Implementation subtotal
Implementation contingency
Implementation total
Recommended Odoo license, year 1
Hardware/third-party placeholder
Estimated first-year total
Recurring annual license only

## BRD Review
Area | Review Finding | Action / Recommendation
Overall | Strong BRD with clear business objectives, KPIs, current-state challenges, scope, roles, functional requirements, non-functional requirements, migration and acceptance criteria. | Use as phase-0 scope baseline, then conduct fit-gap workshops.
Scope | In scope includes CRM, memberships, court scheduling, programs, POS, inventory, purchasing, accounting, payroll, reporting, documents and communications. | Treat as multi-phase ERP implementation; avoid one-shot go-live.
Configuration-first principle | BRD explicitly prefers standard Odoo configuration before customization. | Use Odoo standard apps first; document every custom gap with business justification.
Largest functional gap | Court scheduling/reservations with double-booking prevention, booking privileges, waitlists, instructor schedules and utilization analytics. | Prototype early and confirm whether Appointments/Planning plus custom module is acceptable.
Financial complexity | Sage 50 migration, opening balances, AR/AP, inventory valuation, bank reconciliation and month-end close are critical. | Assign dedicated accounting SME and perform mock financial reconciliation.
Payroll complexity | BRD requires payroll calculations, leave balances and GL posting. | Confirm US payroll compliance/provider strategy before final implementation scope.
Data migration | Customer, household, vendor, inventory, membership, AR/AP, GL and employee data migration are required. | Request sample exports immediately; define cleansing ownership.
Acceptance criteria | BRD includes UAT, financial reconciliation, scheduling validation, POS testing and 30-day stabilization. | Build formal UAT scripts and sign-off gates into project plan.

## Fit Gap
Workstream | Likely Odoo Apps | Fit Level | Key BRD Needs | Complexity | India Delivery Recommendation
CRM & Customer Master | Contacts, CRM, Documents | Partial configuration | Duplicate detection, family/household links, customer lifetime history, document attachment rules | Medium | Configure contacts/customer hierarchy; add custom fields/views for family/household and membership context.
Membership Management | Subscriptions, Sales, Invoicing, Portal | Partial/custom | Membership types, privileges, renewals, guest rules, automatic billing, member statements | High | Use subscriptions for recurring billing; customize privileges and reservation rules.
Court Scheduling | Appointments, Planning, Calendar, Portal | Custom-heavy | Court resources, conflict prevention, recurring reservations, waitlist, maintenance blocks, member booking windows | Very High | Build prototype as first high-risk sprint.
Programs / Lessons / Leagues | Planning, Events, Sales, Project | Partial/custom | Private/group lessons, clinics, league scheduling, attendance and instructor assignments | High | Define program templates and scheduling rules in fit-gap.
Point of Sale | POS, Barcode, Sales, Payments | Mostly standard | Barcode scanning, member pricing, discounts, returns, gift cards, payment processing | Medium | Confirm hardware and processor compatibility.
Inventory & Purchasing | Inventory, Purchase, Barcode, Accounting | Mostly standard | Receiving, adjustments, valuation, reorder rules, PO/vendor bill matching | Medium | Configure product categories, stock locations and valuation method.
Accounting | Accounting, Invoicing, Approvals | Mostly standard | AR/AP, GL, bank reconciliation, reminders, approvals, statements | Medium | Map Sage 50 chart of accounts and closing process.
Payroll & HR | Employees, Time Off, Payroll/Provider | Partial/custom/provider | Payroll calculation, leave balances, GL posting, approvals | High | Confirm US payroll compliance and provider/API.
Reporting | Spreadsheet BI, Dashboards, Accounting Reports | Partial configuration | Executive dashboards, court utilization, memberships, instructor productivity, inventory, financials | Medium | Define KPI formulas and dashboard mockups.
Documents & Waivers | Documents, Sign, Contacts | Mostly standard | Waivers, contracts, correspondence attached to customer records | Medium | Use document workspaces and Sign templates where possible.
Customer Portal / Online Booking | Portal, Website, Appointments | Partial/custom | Real-time account access, optional online reservations, notifications | High | Confirm if online booking is phase 1 or later.
Security & Approvals | Users, Groups, Approvals | Configuration | General Manager, Pro Shop/Accounting, Front Desk/POS, least privilege and approvals | Medium | Create role matrix and test with users.

## Implementation Cost
WBS | Workstream | BRD Coverage | Scope Included | Odoo Apps / Components | Low Hours | Base Hours | High Hours | Risk | Notes | Base Cost USD | Base Cost INR
DISC | Discovery, BRD validation & solution blueprint | All sections | Process workshops, fit-gap, traceability, solution design, backlog and project plan | Project, Knowledge | 60 | 90 | 120 | Medium | India remote workshops; onsite travel excluded.
PM | Project management & governance | All workstreams | Status meetings, RAID, change control, steering reviews, budget/schedule management | Project | 55 | 80 | 110 | Medium | Remote governance.
BASE | Base Odoo setup & environment configuration | NFR, Security, Maintainability | Company setup, fiscal settings, users, email templates, system parameters, backup/cutover settings | Settings, Discuss, Documents | 35 | 50 | 70 | Low | Odoo.sh/on-prem hosting excluded unless selected.
CRM | CRM, customer records & family relationships | BR-CRM-001 to BR-CRM-005 | Customer master, duplicate controls, family links, archive rules, history, communications, documents | CRM, Contacts, Documents | 95 | 135 | 180 | High | Family/household logic may require custom fields.
MEM | Membership management & recurring billing | BR-CRM-006, Membership scope | Membership types, privileges, annual/monthly billing, renewals, guest handling, balances, statements | Subscriptions, Invoicing, Sales | 90 | 130 | 175 | High | Use subscriptions; customize privilege logic.
COURT | Court scheduling & reservations | BR-COURT-001 to BR-COURT-006 | Courts/resources, calendar, recurring bookings, booking windows, conflict prevention, maintenance blocks, waitlists | Appointments, Planning, Calendar, Portal | 170 | 240 | 330 | High | Largest custom-risk area.
PROG | Programs, instruction, lessons, clinics & leagues | Programs and Instruction scope | Private/group lessons, clinics, junior/adult programs, league administration, attendance, instructor assignment | Planning, Events, Sales, Project | 110 | 155 | 220 | High | League scheduling may need custom rules.
POS | Point of Sale retail operations | BR-POS-001 to BR-POS-006 | POS, barcode scanning, member pricing, discounts, gift cards, returns/exchanges, payment flow | POS, Sales, Payments | 75 | 105 | 145 | Medium | Payment terminal provider excluded.
INV | Inventory & purchasing | BR-INV-001 to BR-INV-006 | Products, SKUs, stock locations, receiving, adjustments, valuation, reorder rules, POs, vendor bill match | Inventory, Purchase, Barcode, Accounting | 95 | 135 | 185 | Medium | Covers retail/teaching/office/maintenance inventory.
ACC | Accounting, AR/AP, GL & bank reconciliation | BR-ACC-001 to BR-ACC-009 | CoA, AR/AP, customer invoices, payments, reminders, vendor bills, approvals, bank reconciliation, reports | Accounting, Invoicing, Approvals | 120 | 165 | 230 | High | Sage 50 reconciliation required.
PAY | Payroll & HR | BR-ACC-010 to BR-ACC-013 | Employee records, payroll rules, leave balances, payroll approval, GL posting, payroll reporting | Employees, Payroll, Time Off | 70 | 105 | 155 | High | US payroll provider/compliance to confirm.
DOC | Documents, waivers, contracts & e-signature | BR-CRM-005, Documentation | Document folders, waivers/contracts, attachment rules, document history, e-sign workflow | Documents, Sign, Contacts | 45 | 70 | 100 | Medium | Use Odoo Sign where possible.
COMMS | Customer portal & communications | Customer experience, Scheduling, Collections | Portal access, emails, payment reminders, schedule notifications, optional online booking readiness | Portal, Website, Email, SMS | 65 | 95 | 145 | High | SMS credits excluded.
RPT | Dashboards, reports & analytics | KPIs, Reporting, NFR-008 | Executive dashboards, court utilization, membership stats, instructor productivity, inventory and financial reports | Spreadsheet BI, Dashboards | 80 | 120 | 170 | Medium | Define KPI formulas.
MIG | Data migration & reconciliation | Section 9 Data Migration | Customers, vendors, inventory, memberships, AR/AP, opening GL, employees, cleansing, validation, reconciliation | Import tools, Accounting, Inventory | 130 | 185 | 270 | High | Depends on export quality.
SEC | Roles, permissions & approvals | Section 6 User Roles, NFR-004 | Role-based access, least privilege, approval workflows and audit controls | Users, Approvals, Security | 45 | 70 | 100 | Medium | Create role matrix.
QA | Testing, UAT & quality assurance | NFR-012, Acceptance Criteria | Unit, integration, migration validation, UAT, POS, scheduling, financial reconciliation, regression testing | Project, Test scripts | 100 | 145 | 210 | High | Formal UAT scripts required.
TRAIN | Training & change management | Documentation, User adoption KPI | Admin/front desk/POS/accounting/instructor workflow training, user guides | Knowledge, eLearning | 65 | 95 | 135 | Medium | Remote training assumed.
GO | Cutover, go-live & 30-day stabilization | Cutover Strategy, Overall Acceptance | Go-live checklist, final migration, freeze window, launch support, 30-day stabilization | All modules | 70 | 105 | 150 | High | Post-go-live support window included.
Implementation subtotal
Contingency
Implementation total

## Odoo License Cost
Setting | Value | Notes
Planning paid internal users | 12 | Editable; BRD has roles but no exact headcount.
Standard annual billing price per user/month USD | 24.9 | Planning rate; confirm final quote.
Standard monthly billing price per user/month USD | 31.1 | Comparison only.
Custom annual billing price per user/month USD | 37.4 | Recommended planning rate.
Custom monthly billing price per user/month USD | 46.8 | Comparison only.
FX rate USD to INR | 83.5 | Editable assumption.
Plan | Included | Billing | Monthly USD | Annual USD | Annual INR Ref | Notes
One App Free | One app only | N/A |  |  |  | Not suitable for this BRD.
Standard | All apps, Odoo Online | Annual |  |  |  | Comparison only; no custom modules/API/Studio.
Standard | All apps, Odoo Online | Monthly |  |  |  | Comparison only.
Custom - Recommended | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Annual |  |  |  | Recommended due BRD customization/integration needs.
Custom | All apps, Odoo Online/Odoo.sh/on-premise, Studio, Multi-Company, External API | Monthly |  |  |  | Comparison only.
Odoo.sh hosting | Hosting for custom modules | Quote required |  |  |  | Not included in license.
Topic | Note
License note | Odoo subscription is a vendor cost, separate from India implementation services.
Billing country | If the license is contracted in India, request an official INR quote from Odoo; if contracted by the US client, use the applicable US quote.
Portal users | Customer/member portal users are not treated as paid backend users for this estimate.
Exclusions | Implementation services, IAP/SMS credits, Odoo.sh hosting, and custom-code maintenance are excluded from license pricing.

## Hardware & Third Party
Category | Item | Qty | Unit Cost USD | Estimated Cost USD | Estimated INR Ref | Notes
POS Hardware | Barcode scanners | 2 | 175 |  |  | Needed for BR-POS-001; client-local procurement.
POS Hardware | Receipt printers | 2 | 300 |  |  | Estimate only.
POS Hardware | Cash drawers | 2 | 150 |  |  | Estimate only.
POS Hardware | Label printer for inventory/barcodes | 1 | 450 |  |  | For SKU/barcode labels.
POS Hardware | POS terminal/tablet/computer allowance | 2 | 850 |  |  | Use existing hardware if compatible.
Payments | Payment terminals | 2 | 0 |  |  | Processor/provider quote required.
Communications | SMS / IAP credits | 1 | 0 |  |  | Excluded from license.
Payroll | US payroll provider/subscription | 1 | 0 |  |  | Provider cost to confirm.
Data | Sage 50 export/support assistance | 1 | 0 |  |  | May be client/vendor task.
Travel | Onsite travel and expenses | 1 | 0 |  |  | Remote India delivery assumed.
Contingency | Hardware contingency | 1 |  |  |  | 10% placeholder contingency.
Total

## Phasing
Phase | BRD Priority | Workstreams | Target Outcome | Base Hours | Cost USD | Cost INR Ref | Notes
Phase 0 | Initiation | Discovery, blueprint, project governance, base setup | Validated scope, backlog and environment readiness |  |  |  | Remote India workshops.
Phase 1 | Core Operations | CRM, memberships, court scheduling, programs, POS, inventory, AR/customer billing | Daily operations ready for UAT |  |  |  | Core operational milestone.
Phase 2 | Financial Management | Purchasing, AP, GL, bank reconciliation, payroll/HR, approvals | Financial and payroll workflows configured |  |  |  | Accounting and security milestone.
Phase 3 | Reporting & Documents | Documents, Sign, communications, portal, dashboards | Dashboards, customer comms and documents live |  |  |  | Portal/booking scope to confirm.
Phase 4 | Migration, QA & Go-Live | Data migration, testing, training, cutover, stabilization | Validated migration, UAT sign-off and go-live |  |  |  | 30-day stabilization included.
Subtotal by phases

## Risks
# | Risk | Impact | Probability | Description | Mitigation | Status
1 | Court scheduler fit | High | High | Odoo does not provide a racquet-court scheduler exactly matching the BRD. | Prototype in phase 0/1; freeze reservation rules early. | Open
2 | Membership privileges and family accounts | High | Medium | Billing, family relationships and booking privileges can become complex. | Create membership catalog and household examples before build. | Open
3 | US payroll compliance | High | Medium | Payroll requirements may require US-specific provider or manual process. | Confirm provider and legal compliance responsibility. | Open
4 | Sage 50/data migration quality | High | High | Data quality may affect timeline and reconciliation. | Request sample exports; run mock migration and cleansing. | Open
5 | POS hardware/payment terminal compatibility | Medium | Medium | Hardware/provider choices affect POS setup. | Confirm hardware list and processor before procurement. | Open
6 | Online booking scope creep | High | Medium | Online booking can expand into website/app development. | Decide phase 1 vs later and define member rules. | Open
7 | Financial reconciliation acceptance | High | Medium | GL, AR, AP and inventory must reconcile before go-live. | Define reconciliation owners and sign-off templates. | Open
8 | Custom development upgradeability | Medium | High | Heavy custom code can affect future Odoo upgrades. | Use configuration/Studio first and document custom modules. | Open
9 | User adoption at front desk | Medium | Medium | Busy front-desk workflows need fast UX. | Prototype check-in, POS and reservations with real users. | Open
10 | India/US time-zone coordination | Medium | Low | Offshore delivery requires structured overlap. | Set fixed overlap window and weekly governance. | Open

## Clarifications
Area | Question / Input Required
User Count | How many paid internal users are required at go-live by role?
Courts | How many courts, court types, operating hours and maintenance block rules are needed?
Booking Rules | What are member booking windows, cancellation rules, guest rules and override permissions?
Online Booking | Is online member court booking required in phase 1 or future phase?
Memberships | List all membership types, prices, billing cycles, privileges and family rules.
Programs | List lesson, clinic, league and tournament formats with pricing and scheduling rules.
Instructor Pay | How are instructor compensation, commissions and payroll calculations handled?
Payroll Provider | Which US payroll provider or compliance process will be used?
Sage 50 | What Sage 50 version/export formats are available for GL, AR/AP, vendors, customers and inventory?
Data Volumes | How many customers, members, vendors, SKUs, invoices, open balances and historical reservations exist?
Payments | Which payment processor and terminals will be used for POS and online payments?
Hardware | How many POS stations, scanners, printers, cash drawers and terminals are needed?
Gift Cards | Are gift cards sold/redeemed today, and how should liability be accounted?
Taxes | What Wisconsin sales tax/accounting rules apply to products, memberships, lessons and services?
Waivers | What waiver/contract templates need e-signature and renewal tracking?
Reports | Which management dashboards are mandatory for go-live?
Acceptance Baselines | Current KPI baselines for check-in time, POS time, court utilization, month-end close and payroll time?
Support | What post-go-live support SLA is expected after 30-day stabilization?
Travel | Is onsite discovery/go-live support required, or is fully remote India delivery acceptable?
Decision Makers | Who signs off on accounting, operations, data migration and UAT?

## Traceability
Requirement ID | Area | Requirement Summary | Fit Category | Cost Treatment
BR-CRM-001 | CRM | Duplicate customer verification | Partial | Included in estimate
BR-CRM-002 | CRM | Contact updates across modules | Partial | Included in estimate
BR-CRM-003 | CRM | Customer interaction history | Partial | Included in estimate
BR-CRM-004 | CRM | Archive inactive customers | Partial | Included in estimate
BR-CRM-005 | Documents | Customer documents/waivers/contracts | Standard/Config | Included in estimate
BR-CRM-006 | Memberships | Recurring membership invoicing | Partial | Included in estimate
BR-COURT-001 | Court Scheduling | Prevent double booking | Custom-heavy | Included in estimate
BR-COURT-002 | Court Scheduling | Membership-based booking rules | Custom-heavy | Included in estimate
BR-COURT-003 | Court Scheduling | Cancellation returns availability | Custom-heavy | Included in estimate
BR-COURT-004 | Court Scheduling | Waitlist notifications | Custom-heavy | Included in estimate
BR-COURT-005 | Court Scheduling | Maintenance/special-event closures | Custom-heavy | Included in estimate
BR-COURT-006 | Court Scheduling | Reservations on instructor/customer/report schedules | Custom-heavy | Included in estimate
BR-POS-001 | POS | Barcode product identification | Standard/Config | Included in estimate
BR-POS-002 | POS | Member pricing and discounts | Standard/Config | Included in estimate
BR-POS-003 | POS/Inventory | Immediate inventory update | Partial | Included in estimate
BR-POS-004 | POS/Accounting | Automatic accounting entries | Partial | Included in estimate
BR-POS-005 | POS | Returns/exchanges with audit history | Standard/Config | Included in estimate
BR-POS-006 | POS/CRM | Customer purchase history | Partial | Included in estimate
BR-INV-001 | Inventory | Receiving updates stock | Standard/Config | Included in estimate
BR-INV-002 | Inventory | Adjustment documentation and audit trail | Standard/Config | Included in estimate
BR-INV-003 | Inventory/Accounting | Continuous valuation | Partial | Included in estimate
BR-INV-004 | Inventory | Physical count reconciliation | Standard/Config | Included in estimate
BR-INV-005 | Inventory/AP | Receipt before vendor bill approval | Partial | Included in estimate
BR-INV-006 | Purchase/AP | 3-way match PO/receipt/vendor bill | Standard/Config | Included in estimate
BR-ACC-001 | Accounting | Billable activities create customer charges | Partial | Included in estimate
BR-ACC-002 | Accounting | Payments update balances/accounting | Partial | Included in estimate
BR-ACC-003 | Accounting | Electronic statements | Partial | Included in estimate
BR-ACC-004 | Accounting | Past-due reminders | Partial | Included in estimate
BR-ACC-005 | Accounting | Credits/write-offs authorization | Partial | Included in estimate
BR-ACC-006 | AP | Vendor invoice approvals | Standard/Config | Included in estimate
BR-ACC-007 | AP | Scheduled vendor payments | Standard/Config | Included in estimate
BR-ACC-008 | AP/Accounting | Vendor payments update accounting | Partial | Included in estimate
BR-ACC-009 | AP | Duplicate vendor invoice detection | Standard/Config | Included in estimate
BR-ACC-010 | Payroll | Compensation calculations | Partial | Included in estimate
BR-ACC-011 | Payroll/Time Off | Leave balance updates | Partial | Included in estimate
BR-ACC-012 | Payroll/GL | Payroll expense GL posting | Partial | Included in estimate
BR-ACC-013 | Payroll | Payroll adjustment approvals | Partial | Included in estimate

## Assumptions
Assumption | Value | Notes
India blended hourly rate USD | 28 | Editable
Contingency % | 10% | Editable
Planning paid users | 12 | Editable in License sheet too
FX USD to INR | 83.5 | Editable planning assumption
Delivery model | Remote India delivery | Onsite travel excluded
Topic | Assumption / Note
Commercial note | This is an India delivery planning estimate in USD with INR reference. It is not a binding quote.
License note | Odoo license is separate from implementation. Final quote should be obtained from Odoo or the selling partner based on billing country.
Scope baseline | The 72-page BRD is the baseline. Detailed discovery can change scope, hours and cost.
Remote delivery | Remote workshops and go-live support assumed. Onsite travel and expenses are excluded.
Data | Client must provide Sage 50/spreadsheet exports, field definitions and business validation owners.
Custom code | Custom development is last resort per BRD; custom modules must be documented and upgrade-safe.
Support | 30-day stabilization included; managed support after that is separate.

## Sources
Source | URL / File | Used For | Notes
BRD PDF | Fox Cities Racquet Club - Odoo Business Requirements Document v1 (1).pdf | Scope, requirements, roles, migration and acceptance criteria | Downloaded from attached file and analyzed locally.
Odoo pricing | https://www.odoo.com/pricing | Odoo plan structure, all-app subscription, paid-user rule and exclusions | Final license quote to be confirmed with Odoo/Odoo partner.
Odoo Success Packs | https://www.odoo.com/pricing-packs | Implementation benchmark and Odoo service scope reference | Used as reference only; India partner estimate uses BRD workstreams.